## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | AI-Powered Knowledge Engine for Smart Support & Ticket Resolution | MUST HAVE | Non | ALL | 3- Completed
S1 | S1 | US-001 | Development of GUI | MUST HAVE | Streamlit | Sirisha | 3- Completed
S1 | S1 | US-001 | Development of Backend Part | MUST HAVE | Non | Sahil | 3- Completed
S1 | S1 | US-001 | Model Fine Tuning and Integration of Models | MUST HAVE | all-MiniLM-L6-v2,Other Python lib. | Raghu | 3- Completed
S1 | S1 | US-001 | For Training The model and the Datasets | MUST HAVE | Non | Rohit | 3- Completed
S2 | S2 | US-002 | Introduced to Real-time Recommendation of solution for tickets | MUST HAVE | Non | ALL | 3- Completed
S2 | S2 | US002 | Creation of Datasets for the real time recommendation | MUST HAVE | Web and Ai models | Sahil & Raghu | 3- Completed
S2 | S2 | US-002 | GUI Area for Real time solutions | MUST HAVE | Streamlit | Rohit & Sirisha | 3- Completed
S2 | S2 | US-002 | Training model for real time solution. | MUST HAVE | Python Lib. | Rohit | 3- Completed
S3 | S3 | US-003 | Introduced to Content Gap Analysis | MUST HAVE | Non | ALL | 3- Completed
S3 | S3 | US-003 | Backend Setup for the log-file Creation and Use Cases | MUST HAVE | Non | Sahil & Raghu | 3- Completed
S3 | S3 | US-003 | GUI for Contact Gap Analysis with visualization | MUST HAVE | Matplotlib,Seaborn,Plotly | Rohit & Sirisha | 3- Completed
S4 | S4 | US-004 | Introduced to Sprint 4 Slack integration and Analytics | MUST HAVE | Non | ALL | 3- Completed
S4 | S4 | US-004 | Slack integration to the back-end to contact with GUI | MUST HAVE | Slack Channel | Sahil | 3- Completed
S4 | S4 | US-004 | Improvement of GUI with Notification With the Slack | MUST HAVE | Non | Raghu & Rohit | 3- Completed
S4 | S4 | US-004 | Improvement of GUI with Analytics Button to have visible track of Tickets | MUST HAVE | Plotly | Sirisha | 3- Completed
S4 | S4 | US-004 | Final Training and discussion of the model | MUST HAVE | Non | ALL | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 64 | 31 | 21 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to project Smart Support & Ticket Resolution | 2025-10-09 | 2025-10-09 | All | Others | 3- Completed | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Discussion on GUI and the Backend development and team assign | 2025-10-11 | 2025-10-12 | All | Build | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Development of GUI And basic Backend | 2025-10-13 | 2025-10-16 | SirIsha,Sahil | Coding | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Planning for the next improved in GUI and how to develop the full Backend | 2025-10-17 | 2025-10-17 | All | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Development of Full GUI And Backend | 2025-10-18 | 2025-10-20 | SirIsha,Sahil | Others | 3- Completed | 5 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Fine Tuning and Model integration | 2025-10-21 | 2025-10-22 | Raghu | Integration Test | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Model training | 2025-10-23 | 2025-10-23 | Rohit | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 8 | Introduction to Real-Time Solution recommendation | 2025-10-27 | 2025-10-27 | All | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 9 | Development od back-end for realtime solutions | 2025-10-28 | 2025-10-30 | Sahil & Raghu | Coding | 3- Completed | 4 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 10 | Datasets for the real time solution | 2025-10-29 | 2025-11-01 | Sahil & Raghu | Build | 3- Completed | 7 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 11 | Gui updated for the real-time Solution with a particular button | 2025-10-29 | 2025-10-30 | SirIsha,Rohit | Design | 3- Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 12 | Model training Over the new Datasets | 2025-11-01 | 2025-11-02 | Rohit | System Test | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 13 | Introduced to Content Gap Analysis Part | 2025-11-03 | 2025-11-03 | All | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 14 | Development of Backend to manage Log file and keep the log of each ticket | 2025-11-04 | 2025-11-05 | Sahil & Raghu | Coding | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 11 | Gui updated for the Content Gap Data and Visualization | 2025-11-04 | 2025-11-06 | SirIsha,Rohit | Design | 3- Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 12 | Introduced to Slack Integration and the analytics Part | 2025-11-07 | 2025-11-07 | All | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 13 | Backend setup for Slack integration | 2025-11-08 | 2025-11-10 | Sahil & Raghu | Coding | 3- Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 14 | Screen optimization for real time changes | 2025-11-09 | 2025-11-10 | Sahil | Design | 3- Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 15 | Gui updated (notification button for slack message ) | 2025-11-09 | 2025-11-11 | Rohit | Design | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 16 | Gui updated (Analytic part for Ticket issue visualization) | 2025-11-10 | 2025-11-10 | SirIsha | Design | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 17 | Final Training Of the model and Dataset Updates | 2025-11-11 | 2025-11-12 | Rohit & Sahil | System Test | 3- Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on J3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on K3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on the overall project goal | Read the project charter and conducted a Q&A session with the Product Owner/Manager
Sprint 1 | Day 5 | Difficulty setting up the initial development environment/API keys | Followed the official documentation and sought help from a senior developer for configuration
Sprint 1 | Day 7 | Stuck on implementing a specific algorithm/feature | Researched alternative methods on Stack Overflow and conducted a spike (time-boxed investigation) before selecting the best approach
Sprint 1 | Day 9 | Encountered unexpected issues when integrating two different modules/libraries | Debugged the code line-by-line and conducted unit tests to isolate the conflict
Sprint 2 | Day 14 | Challenges in writing comprehensive tests that meet the required coverage percentage | Attended a workshop/read a tutorial on advanced testing techniques (e.g., mocking/stubbing) and applied them to my code
Sprint 2 | Day 16 | Not sure about the best way to handle asynchronous operations/state management | Discussed design patterns with the team lead and aligned on a standard approach
Sprint 3 | Day 18 | Lack of clear understanding of deployment pipeline/CI/CD process | Paired with the DevOps engineer to walk through the deployment steps and documented the process
Sprint 3 | Day 19 | Needed to improve the performance of a slow-running query or function | Used performance profiling tools to identify bottlenecks and implemented necessary optimizations
Sprint 3 | Day 20 | No Clarity about agile sheet | Discussed with mentor She guided me properly
Sprint 4 | Day 24 | No Proper idea about slack real time notification | Searched web discussed with teammates and with mentor
Sprint 4 | Day 25 | Still not much clear about the Real time notification | Discussed with mentor She guided me practically to have a better understanding
Sprint 4 | Day 27 | How to improve the model in user friendly way | Added a Real time screen optimization
Sprint 4 | Day 28 | What are things that should be uploaded the git | Attended the meeting mentor guided everyone for that

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-10-09 | 2025-10-23 | Raghu,Sahil,Sirisha | logic check | Wasting time on Other Things | Improvements in GUI | Discussed with my teammate on meeting about related improvements
2 | Sprint 2 | 2025-10-27 | 2025-11-02 | Raghu,Sahil,Sirisha | Improving the way of presentation | Delaying on the project tasks | Improving Datasets | Asked questions with the mentor and discussed with the team in term of improvements
3 | Sprint 3 | 2025-11-03 | 2025-11-06 | Raghu,Sahil,Sirisha | Revising SQL | Leaving the concept less cleared | Bug fixes | Giving more time on practice,learning and understanding(asking with mentors and team)
4 | Sprint 4 | 2025-11-07 | 2025-11-12 | Raghu,Sahil,Sirisha | Learning about Third Party Integration | Revising SQL | Learning and practice of integration | Conducted discussion on the topic and completed the project on time.